## Action Summary
Combat Cognition — Unresolved Evaluation-Action Register
Decision freeze for the P001 jab-only laptop-camera feasibility case. No thesis prose.
Register date | 2026-08-01
Total actions | 12
Closed / complete | 4
Open—bounded | 8
Additional data required now | 0
New participants required now | No
New recordings required now | No
Scope expansion | None
Decision rule | Proceed condition | Evidence boundary | P001 treatment | Model treatment | Software treatment | Media treatment | Next protocol gate
Unobtainable evidence is disclosed, not invented | All open items have explicit limitation/future-work handling | No combined overall accuracy | Expert self-evaluation only | Benchmark/generated/model-only metrics remain labelled | Tests establish verification, not task accuracy | Screenshots restricted; videos excluded | Finalize figures, tables and appendices

## Evaluation Actions
action_id | claim_link | evidence_gap | current_evidence | disposition | before_chapter_planning | required_handling | uses_existing_evidence_only | prohibited_claim | status
EA01 | C01 | Independent landmark and jab-form accuracy | No blinded landmark/form labels exist for P001. | Limitation + future evaluation | Not required for bounded feasibility conclusion | Disclose that operation/screenshots show function, not accuracy; propose independent frame annotation later. | No | Population or application accuracy | Open—bounded
EA02 | C02 | Real jab-domain ACP evaluation and component ablation | ACP is evaluated on participant-held-out Human3.6M-17; no grouped jab ground truth or ablation. | Limitation + future evaluation | Not required for benchmark-specific prototype conclusion | Report benchmark/domain gap and avoid attributing gains to individual components; defer grouped jab evaluation/ablation. | No | Jab prediction validity or component causality | Open—bounded
EA03 | C03 | Last-pose and constant-velocity baselines | Frozen ACP package reports both baselines and per-horizon errors. | Completed from existing evidence | Complete | Retain benchmark-specific normalized metrics and relative error reductions. | Yes | Millimetres, jab-domain or state-of-the-art performance | Closed
EA04 | C04 | Real annotated phase and boundary evaluation | Phase metrics use generated bootstrap data; P001 has no frozen independent framewise phase labels. | Limitation + future evaluation | Not required for generated-pipeline conclusion | Label metrics as generator-defined pipeline evidence; defer grouped real annotated boundary evaluation. | No | Real-jab phase accuracy | Open—bounded
EA05 | C06 | Rule-only versus hybrid end-to-end comparison | Historical export has no verified experimental-condition label. | Limitation + future evaluation | Not required for implemented-framework feasibility | Do not reconstruct conditions retrospectively; report absence and defer a condition-labelled replay. | No | Comparative coaching benefit or causal effect | Open—bounded
EA06 | C08 | Independent validation of jab variables and thresholds | P001 traces support multi-joint variables, but thresholds are researcher-authored. | Limitation + future evaluation | Not required for expert-informed prototype description | Describe thresholds as expert-authored implementation choices; defer independent expert/sensor triangulation. | No | Universal or clinically validated thresholds | Open—bounded
EA07 | Cross-cutting | End-to-end latency and frame-rate measurement | Only model-only ONNX latency exists; export contains zero response-time observations. | Limitation + future evaluation | Not required for model-only latency claim | Keep ACP/phase latency labelled model-only; defer camera-to-feedback timing on the same laptop. | No | Real-time full-system performance | Open—bounded
EA08 | Cross-cutting | Structured usability ratings | No structured P001 usability instrument was captured. | Limitation + future evaluation | Not required for descriptive expert self-evaluation | Use supplied commentary only as qualitative expert observation; do not invent retrospective scores. | No | Participant usability or satisfaction score | Open—bounded
EA09 | Cross-cutting | Canonical, rule-engine and repetition-row inconsistency | practice-42 preserves 3 canonical reps, 0 rule-engine reps and one implausible-duration repetition row. | Completed as failure-mode evidence | Complete | Retain and report the discrepancy; do not repair or harmonize the historical evidence. | Yes | Perfect integration or internally consistent persistence | Closed
EA10 | Cross-cutting | Generalization beyond P001, jab and laptop camera | Available controlled evidence is intentionally limited to one researcher-expert case. | Limitation + future evaluation | Not required for n=1 expert feasibility conclusion | Freeze scope; defer additional people, techniques, viewpoints and devices. | No | Population effectiveness or cross-technique generalization | Open—bounded
EA11 | Cross-cutting | Operational LLM evaluation | Implementation audit found deterministic rule/template feedback and no operational OpenAI LLM. | Not applicable to current artifact | Complete | Evaluate and describe the deployed deterministic coaching layer; keep any LLM comparison as future work only. | Yes | Current LLM operation, intelligence or benefit | Closed—not applicable
EA12 | Cross-cutting | Private recordings in report | User requires recordings to remain private and excluded. | Protocol constraint | Complete | Use derived anonymized screenshots/data only where allowed; do not insert video into report artifacts. | Yes | Video-based report evidence | Closed—constraint

## Chapter Gate Checklist
gate_id | gate | status | evidence_or_next_action
G01 | Claim reconciliation frozen | Complete | Four supported-with-boundary; five partially supported; no unsupported claims
G02 | Baseline requirement checked | Complete | Last-pose and constant-velocity evidence already frozen in ACP package
G03 | Missing empirical evidence dispositioned | Complete | EA01, EA02, EA04–EA08 and EA10 become explicit limitations/future evaluation
G04 | Integration discrepancy retained | Complete | EA09 preserved as failure-mode evidence
G05 | Operational reasoning identity controlled | Complete | EA11 confirms deterministic rule/template artifact; LLM evaluation not applicable
G06 | Participant/technique/camera scope frozen | Complete | P001 only; jab only; laptop camera
G07 | Media handling frozen | Complete | Screenshots restricted; videos private and excluded
G08 | Figures/tables/appendices finalized | Next | Preparation step 3
G09 | University-format chapter plan and claim approval | Pending | Preparation step 4; thesis writing still prohibited

## Evidence Locks
lock_id | evidence_area | frozen_interpretation | prohibition
L01 | Authoritative participant | P001 researcher/developer/martial-arts expert | Do not relabel as independent participant
L02 | Technique/device | Jab only; laptop camera | Do not generalize to other techniques/devices
L03 | Confirmed case | practice-42; 3 clusters; 250 frames; 8.3 s; 96% tracking; 22 decoder changes | Self-validation, not ground truth
L04 | Database | Full history retained but historical/outlier records excluded from headline case | Do not compute aggregate accuracy
L05 | ACP | Human3.6M-17 benchmark with simple baselines and normalized metrics | Not live jab or physical-unit evidence
L06 | Phase | Generated bootstrap metrics | Not real-jab phase accuracy
L07 | Latency | ONNX model-only | Not camera-to-feedback latency
L08 | Feedback | Deterministic rule/template | No operational OpenAI LLM
L09 | Media | Screenshots restricted; recordings private and excluded | Do not insert videos